LACONIA PROJECT UPDATES – JULY, 2025

# LACONIA ROAD PROJECTS

Current: The surface asphalt coat on Hilliard Road is scheduled for paving the week of July 28th. Appleton St reconstruction will be completed in the first week of August. The Contractor will begin work on Old North Main Street after Appleton St is complete.  Old North Main St’s reconstruction is from Village Court to Parade Road.  Road work scheduled for this fall includes reclaiming and drainage improvements on Morningside Drive, Larkwood Dr and Windmill Lane. White Oaks Road phase 2 will take place after Labor Day.

Communication Plan: Letters will soon be going out to those on roads who need to be reached out to directly. Typically, this is for roads being reconstructed or reclaimed.

Previous:  Hilliard Road base paving has been completed. Cleanup, loaming and seeding will occur after Bike Week. The topcoat of asphalt on Hilliard Road will take place this summer. White Oaks Road sewer extension phase 1 has been completed and has been base paved. Cleanup will be completed after Bike Week. White Oaks Road phase 2 will take place after Labor Day. White Oaks Road’s asphalt topcoat will be placed in 2026 before MC week. The contractor is beginning work on Appleton Street’s reconstruction and drainage improvements. After completing Appleton Street, they will begin reconstruction of the north end of Old North Main St and Morningside Drive.

CENTENARY AVENUE BRIDGE

Current: Laconia DPW, HEB Engineers and NHDOT are struggling with the NH DOT Railroad Bureau to get a temporary use agreement to conduct survey work within the RR ROW.

Communication Plan: The next meeting will occur later than was anticipated due to the updated engineering study. The next public meeting will be held late summer of 2025. At this meeting Public Works and the consultant will present the results of the study to include the analysis of options for the northern at grade crossing with some preliminary engineering.

Previous:  HEB Engineers is struggling with NH Railroad in getting the necessary permissions to complete the survey within the RR ROW.

MILL STREET PEDESTRIAN BRIDGE

Current: DPW is expecting HEB, the engineer consultant, to provide by mid-August an existing features plan, conceptual design drawings for the bridge replacement, and the engineer’s opinion of probable cost.

Communication Plan: Letters were sent to all abutters notifying them of the survey and of the bore sampling. Public Works is managing this project using NHDOT’s locally managed project process. Therefore, the study phase will include a public information meeting to seek feedback on the project. Once the study phase is complete, Public Works will schedule another public information meeting to present the project’s proposed alternatives.

Previous:  HEB’s Preliminary Engineering is ongoing.

HILLIARD ROAD CULVERT CROSSING

Current:  HEB engineers will complete the “predesign phase” of this project by September 2025.

Communication Plan: Public Works is managing this project using NHDOT’s locally managed project process. Therefore, the study phase will include a public information meeting to seek feedback on the project. Once the study phase is complete, Public Works will schedule another public information meeting to present the proposed alternatives of the project to the public.

Previous:  No change.

WEIRS BLVD / US ROUTE 3 BRIDGE

Current: Hoyle Tanner and DPW are awaiting Brady Sullivan’s revised turn lane plan to incorporate it into the final design of the bridge project. The project is on schedule to go out to bid in February 2026 for a fall of 2026 construction. The plan is to use accelerated bridge construction techniques and to close Weirs Blvd to through traffic at the bridge.

Communication Plan: The project requires temporary construction easements. Public Works and the consultant will be meeting with individual property owners to obtain these easements.

Previous:  A deficiency in the bridge’s deck was discovered on Friday June 6th. An onsite meeting  with DPW, Hoyle Tanner’s Engineer, Evroks and Busby was held to develop a repair plan until the bridge is replaced in the fall of 2026. In the meantime, the crossing over the bridge has been widened and restriped with barricades to keep traffic away from the section of the deck that is weak. DPW and NHDOT reviewed the project scope on June 12th and there were no issues.

ELM STREET TRANSPORTATION ALTERNATIVE PROJECT

Current: DPW is expecting the preliminary design by December 2025.

Communication Plan: This project is currently scheduled for 2028 NHDOT funding.

Previous:  NHDOT has approved the updated scope of engineering.

OPECHEE LOOP

Current: The project has been awarded to ED Swett. Construction will start in late August of this year. The project will be completed by mid-November.

Communication Plan: Public Works will work with the area’s business owners to minimize impact to their businesses.

Previous:  The project has been awarded to ED Swett and will take place in late August of this year. The project will be completed by mid-November.

# LACONIA DOWNTOWN TIF DISTRICT

Current:  Contractor is working on our Streetscape Project.  We are also out to bid for the Pumpkin Festival Lighting Project Downtown.

Previous:  Scheduled for a Public Hearing at the City Council’s June 23rd meeting for additional funds for Streetscape Project and Pumpkin Festival Support.

# LACONIA LAKEPORT TIF DISTRICT

Current:  No update.

Previous: No update.

WEIRS TIF DISTRICT

Current:  Working on an RFP for a Structural Analysis of the Weirs Boardwalk.

Previous:  No update.

# WINNIPESAUKEE RIVER BASIN PROJECT

Current:  The WRBP Advisory Board decided not to support two clean water revolving loan requests due to delays and issues with other WRBP projects.  The Board has proposed a change to the state law on the replacement fund.  The objective is to submit an LSR in September for the upcoming Legislature year.  If the change is approved by the legislature and signed by the Governor, the change will take effect sometime in 2026.

Previous:  The WRBP Administrator provided the rate allocation adjustments that take effect on July 1st.  Laconia’s operations and maintenance account rate increases from 43.31% to 43.32%. The Administrator at the June 16th Board meeting stated that EPA’s funding for the clean water revolving road fund will be reduced significantly. This will reduce the amount of funds available to NHDES resulting in low interest loans being limited to projects NHDES considers high priority.

# SEWER COLLECTION SYSTEM

Current:  The annual cleaning and camera inspection of 20% of the sewer mains has begun. The work will occur over the next two months.

Communication Plan: DPW will be making direct contact with all property owners in the project area to coordinate connecting the houses to the City sewer system if their building is within 250 feet of a City sewer main and they are not eligible for a waiver.

Previous:  Phase 1 of the sewer extension project on White Oaks Rd has been completed. The pump station will soon be commissioned. The project is on schedule. The goal is for the sewer extension and the sewer pump station to be online before Lady of the Lakes submits their first CO.

# WEIRS BEACH DOCK RECONFIGRATION AND REHABILITATION PROJECT

Current:  The project has reached final completion. An additional scope of cosmetic work is being generated for this Fall.

Communication Plan: Public Works will coordinate with the General Manager of the Mount Washington Cruise Line and the Weirs Action Committee during the project.

Previous:  Final completion is scheduled for the end of June. A list of additional requests from DPW has been submitted to the contractor to be completed this fall. These requests are mostly cosmetic and include replacing some of the pressure treated stair treads on the stairs from the boardwalk to the dock.

# WEIRS BEACH RESTORATION

Current:  No update.

Area Impacted: Weirs Beach

Communication Plan: This project will be done in the off season to keep the impacts low. The local newspaper will be notified, as well as the newspapers in northern Massachusetts. This will help spread the word to those who use the area the most.

Previous:  No update.

# LACONIA MASTER PLAN UPDATE

Current:  Out to bid for our Master Plan, submittals are due to the City by the end of July.

Previous:  No update.

LACONIA STATE SCHOOL UPDATE

Current: The City Manager will provide an update at the July 28, 2025 City Council meeting.